## Agile-TRLs
Technology Readiness Levels (TRLs)
Hardware |  |  |  | Software |  |  |  | Agile
TRL | Definition | Description | Supporting Information | TRL | Definition | Description | Supporting Information | TRL | Definition | Description | Supporting Info.
1 | Basic principles observed and reported. | Lowest level of technology readiness. Scientific research begins to be translated into applied research and development (R&D). Examples might include paper studies of a technology's basic properties. | Published research that identifies the principles that underlie this technology. References to who, where, when. | 1 | Basic principles observed and reported. | Lowest level of software technology readiness. A new software domain is being investigated by the basic research community. This level extends to the development of basic use, basic properties of software architecture, mathematical formulations, and general algorithms. | Basic research activities, research articles, peer-reviewed white papers, point papers, early lab model of basic concept may be useful for substantiating the TRL. | 1 | Basic principles questioned, explored, and investigated | Lowest level of technology readiness. A new, advanced, or enhanced system or software technology is investigated by research scientists, engineers, and innovators. Examples include initial enterprise, mission, or customer needs and possible solutions. | • System feasibility plan. • Initial product backlog. • Initial estimates done.
2 | Technology concept and/or application formulated. | Invention begins. Once basic principles are observed, practical applications can be invented. Applications are speculative, and there may be no proof or detailed analysis to support the assumptions. Examples are limited to analytic studies. | Publications or other references that outline the application being considered and that provide analysis to support the concept. | 2 | Technology concept and/or application formulated. | Once basic principles are observed, practical applications can be invented. Applications are speculative, and there may be no proof or detailed analysis to support the assumptions. Examples are limited to analytic studies using synthetic data. | Applied research activities, analytic studies, small code units, and papers comparing competing technologies. | 2 | Technology concept and/or application examined, studied, and formulated | Once basic technological alternatives and solutions are identified, creation and realization of practical applications can be planned, started, and executed. Examples may include conceptual models, wireframes, or paper prototypes. | • Whiteboard model. • Brainstorming results. • Conceptual designs.
3 | Analytical and experimental critical function and/or characteristic proof of concept. | Active R&D is initiated. This includes analytical studies and laboratory studies to physically validate the analytical predictions of separate elements of the technology. Examples include components that are not yet integrated or representative. | Results of laboratory tests performed to measure parameters of interest and comparison to analytical predictions for critical subsystems. References to who, where, and when these tests and comparisons were performed. | 3 | Analytical and experimental critical function and/or characteristic proof of concept. | Active R&D is initiated. The level at which scientific feasibility is demonstrated through analytical and laboratory studies. This level extends to the development of limited functionality environments to validate critical properties and analytical predictions using non-integrated software components and partially representative data. | Algorithms run on a surrogate processor in a laboratory environment, instrumented components operating in a laboratory environment, laboratory results showing validation of critical properties. | 3 | Analytical and experimental proof of concept of critical functions and characteristics | Active R&D is initiated. The level at which operational feasibility is demonstrated with physical hardware and software models. Examples include initial hardware and software spikes, Iteration zero activities, and other preplanning activities before actual iterations begin. | • Exploratory code spike. • Iteration zero results. • What-if code builds.
4 | Component and/or breadboard validation in a laboratory environment. | Basic technological components are integrated to establish that they will work together. This is relatively "low fidelity" compared with the eventual system. Examples include integration of "ad hoc" hardware in the laboratory. | System concepts that have been considered and results from testing laboratory-scale breadboard(s). References to who did this work and when. Provide an estimate of how breadboard hardware and test results differ from the expected system goals. | 4 | Module and/or subsystem validation in a laboratory environment (i.e., software prototype development environment). | Basic software components are integrated to establish that they will work together. They are relatively primitive with regard to efficiency and robustness compared with the eventual system. Architecture development initiated to include interoperability, reliability, maintainability, extensibility, scalability, and security issues. Emulation with current/legacy elements as appropriate. Prototypes developed to demonstrate different aspects of eventual system. | Advanced technology development, stand-alone prototype solving a synthetic full-scale problem, or standalone prototype processing fully representative data sets. | 4 | Larger functionality, operational slice, or mission thread validated using laboratory simulations | Basic system hardware and software technology components are integrated to establish that they will work together. Evaluation is limited to essential operational or functional testing, versus the full range of non-functional tests. Examples include an essential system function, slice, or mission thread, feature, or key characteristics of multiple features. | • One or more iterations. • Code slice or thread. • Up to one code release.
5 | Component and/or breadboard validation in a relevant environment. | Fidelity of breadboard technology increases significantly. The basic technological components are integrated with reasonably realistic supporting elements so they can be tested in a simulated environment. Examples include "high-fidelity" laboratory integration of components. | Results from testing laboratory breadboard system are integrated with other supporting elements in a simulated operational environment. How does the "relevant environment" differ from the expected operational environment? How do the test results compare with expectations? What problems, if any, were encountered? Was the breadboard system refined to more nearly match the expected system goals? | 5 | Module and/or subsystem validation in a relevant environment. | Level at which software technology is ready to start integration with existing systems. The prototype implementations conform to target environment/interfaces. Experiments with realistic problems. Simulated interfaces to existing systems. System software architecture established. Algorithms run on a processor(s) with characteristics expected in the operational environment. | System architecture diagram around technology element with critical performance requirements defined. Processor selection analysis, Simulation/Stimulation (Sim/Stim) Laboratory buildup plan. Software placed under configuration management. Commercial-off-the-shelf/government-off-the-shelf (COTS/GOTS) components in the system software architecture are identified. | 5 | Function, slice, or thread evaluated using passive or active operational data | Level and fidelity of system hardware and software technology maturity increases significantly. Technologies move well beyond conceptual, feasibility, and operational stages, and are ready for functional and non-functional testing allocated to them. Synthetic and/or other laboratory data may still be in use for test and evaluation purposes. | • One or more releases. • Feature slice or thread. • Feature tests passed.
6 | System/subsystem model or prototype demonstration in a relevant environment. | Representative model or prototype system, which is well beyond that of TRL 5, is tested in a relevant environment. Represents a major step up in a technology's demonstrated readiness. Examples include testing a prototype in a high-fidelity laboratory environment or in a simulated operational environment. | Results from laboratory testing of a prototype system that is near the desired configuration in terms of performance, weight, and volume. How did the test environment differ from the operational environment? Who performed the tests? How did the test compare with expectations? What problems, if any, were encountered? What are/were the plans, options, or actions to resolve problems before moving to the next level? | 6 | Module and/or subsystem validation in a relevant end-to-end environment. | Level at which the engineering feasibility of a software technology is demonstrated. This level extends to laboratory prototype implementations on full-scale realistic problems in which the software technology is partially integrated with existing hardware/software systems. | Results from laboratory testing of a prototype package that is near the desired configuration in terms of performance, including physical, logical, data, and security interfaces. Comparisons between tested environment and operational environment analytically understood. Analysis and test measurements quantifying contribution to system-wide requirements such as throughput, scalability, and reliability. Analysis of human-computer (user environment) begun. | 6 | Critical system features developed and evaluated using passive or active data | Representative system-level model or prototype containing most if not all of one or more critical system features satisfying high-priority customer or end-user needs and business or mission value. Features satisfy critical functional and non-functional tests using simulated or passive operational data. | • Main features released. • System slice or thread. • Multiple code releases.
7 | System prototype demonstration in an operational environment. | Prototype near or at planned operational system. Represents a major step up from TRL 6 by requiring demonstration of an actual system prototype in an operational environment (e.g., in an aircraft, in a vehicle, or in space). | Results from testing a prototype system in an operational environment. Who performed the tests? How did the test compare with expectations? What problems, if any, were encountered? What are/were the plans, options, or actions to resolve problems before moving to the next level? | 7 | System prototype demonstration in an operational, high-fidelity environment. | Level at which the program feasibility of a software technology is demonstrated. This level extends to operational environment prototype implementations, where critical technical risk functionality is available for demonstration and a test in which the software technology is well integrated with operational hardware/software systems. | Critical technological properties are measured against requirements in an operational environment. | 7 | Critical system features, functions, and capabilities evaluated using operational data | System-level model or prototype demonstrating most user needs associated with one or more critical system features. Features satisfy most functional and non-functional tests allocated to them, preferably using live operational data. | • Most features released. • Release plan on-time. • Development tests pass.
8 | Actual system completed and qualified through test and demonstration. | Technology has been proven to work in its final form and under expected conditions. In almost all cases, this TRL represents the end of true system development. Examples include developmental test and evaluation (DT&E) of the system in its intended weapon system to determine if it meets design specifications. | Results of testing the system in its final configuration under the expected range of environmental conditions in which it will be expected to operate. Assessment of whether it will meet its operational requirements. What problems, if any, were encountered? What are/were the plans, options, or actions to resolve problems before finalizing the design? | 8 | Actual system completed and mission qualified through test and demonstration in an operational environment. | Level at which a software technology is fully integrated with operational hardware and software systems. Software development documentation is complete. All functionality tested in simulated and operational scenarios. | Published documentation and product technology refresh build schedule. Software resource reserve measured and tracked. | 8 | System features, functions, and capabilities completed, validated, and delivered for use | System representation satisfying all functional and non-functional requirements allocated to a backlog and given release plan. Features satisfy all functional and non-functional, as well as final acceptance tests using live operational data. | • Product backlog done. • Release plan complete. • Acceptance tests pass.
9 | Actual system proven through successful mission operations. | Actual application of the technology in its final form and under mission conditions, such as those encountered in operational test and evaluation (OT&E). Examples include using the system under operational mission conditions. | OT&E reports. | 9 | Actual system proven through successful mission-proven operational capabilities. | Level at which a software technology is readily repeatable and reusable. The software based on the technology is fully integrated with operational hardware/software systems. All software documentation verified. Successful operational experience. Sustaining software engineering support in place. Actual system. | Production configuration management reports. Technology integrated into a reuse "wizard." | 9 | [Legacy] system undergoing performance tuning, refinement, enhancement, and extension | One or more systems, branches, or variants created to optimize system performance, fix or address critical operational faults and failures, or provide significant enhancements and block upgrades to satisfying emerging market, enterprise, or operational mission needs. | • Multiple releases done. • Have operational data. • Performance tuning.